Diversity Living Services (DLS) is a long-established (2002)  charitable company ( registered as a company Limited by Guarantee and Charity)  embedded in the disadvantaged (Black, Asian, Migrants, Minority Ethnic and (BAMER)  and other communities in our catchment area – communities which are often seen as hard-to-reach by public authorities.

We are based in the London Borough of Enfield and  serve our catchment area  of North London. We have vast experience in working with these communities to identify and support their needs.

Our aim is to promote equality and diversity by supporting (BAMER) communities in accessing services and opportunities through advice, training, advocacy, participation and engagement with mainstream services.

Our objectives:

• Promote social integration, equality and inclusion by raising public awareness and challenging

discrimination and social exclusion against disadvantaged BAMER people;

• Provide independent and confidential information, advice, guidance and support on welfare rights,

equality, human rights, training, housing, employment and legal issues

• Promote good health and wellbeing through community training and awareness about health,

employability skills, and access to services and opportunities

• Support young people in accessing services and opportunities including employment, entrepreneurship, arts, education, housing and social support

• Promote and develop the capacity of young people by building on their skills and aptitudes for their

personal growth and their community’s long-term success and development

• Represent our service users in decision-making and consultations to ensure they reflect the makeup

of local communities

Currently we have 4 paid staff and 15 unpaid staff (volunteers), and we have recently trained and mentored 120 youth learners. We are a social

barometer of our communities, continually adapting and developing our provision to meet emerging and current need. To sustain our organisation, over the years we've been supported by funding from  London  Councils, Lottery Funds, Trusts, Foundations and private donations for projects and core activity. The

chief officer  and founder Ernest Rukangira is hugely skilled and experienced in developing and managing multiple projects - and achieving targets – providing services and support to BAMER communities. Ernest has a Masters in Chemistry and another one in Development Studies ( SOAS, University of London). He is a former teacher (College of further education ) of Maths, Physics and Chemistry.

Other employees include one with Masters in Public Health from University College London (UCL)  and another one in Nutrition and public Health from Westminster University.

DLS is currently implementing an Erasmus+ Strategic Partnerships Key Action 2 project that involved 5 partners. The partners involved in this project   have experience in implementing Erasmus+ Eram Strategic Partnerships Projects.

DLS has  vast experience of implementing projects funded by UK trusts and

foundations and public authorities. Our current  Health project being implemented and funded by National Lottery Community Fund ( budget of £450,000 for 5 years) aims  to prevent poor health

within BAMER (including the youth) communities. With this funding from this project  we have developed experience in producing and designing  education materials for training BAMER communities about health issues. Other programmes ( including research projects) targeting young people  have been funded London Community Foundation,  The Refugee Council, City Bridge Trust and the Mayor of London and the Mayor of London.

DLS is a member major UK Networks of charities and voluntary organizations including the Refugee Council and the National Council for Voluntary Organizations ( NCVO). DLS is also a member of Healthwatch Enfield Reference Group and participate regularly in  consultations and meetings  about London residents’ health issues organized by London Councils, Enfield Council Public Health, NHS Enfield Clinical Commissioning Group and Middlesex

University Hospital.

Project Description:

Please explain the context and the objectives of your project as well as the needs and target groups to be addressed. Why should this project be carried out transnationally?

This project targets disadvantaged young people with fewer opportunities as those aged between 13 and 25 years in Europe, particularly in Albania, Bulgaria and UK.

According to  WHO  Europe ( 2010)  young people with that age is a priority group for health care providers. This  age can be a period of high risk for the development of mental illness, and a time when some young people may experiment with risky drinking, smoking or illicit drug use, become less active or eat more unhealthy food and

### drinks. These behaviours are established as a young person and go on to become the lifestyles of adults leading to chronic health problems. Additionally, marginalised young people can have greater difficulty in accessing health information, services and need support to navigate the health system. According to UK NHS (2009), young people may be unaware of their problems, afraid to seek help, or unable to make positive change without help, particularly in relation to  obesity, mental health, accessing sexual and reproductive health. According to AstraZeneca ( Lancet, 2012), about 70% of premature deaths in adults can be linked back to behaviours that started in adolescence. Addressing these behaviours when young can be far more effective than later in life.

According to EU Youth policies in Bulgaria (2018), Bulgaria is one of the member-states with the highest overweight and obesity levels amongst young people in the entire EU. The policies recommend the Albanian Government and other stakeholders to increase awareness  among the youth about healthy lifestyles.

Recent media reports ( The Guardian and BBC) suggest that the COVID-19 has contributed to motivating young people in becoming more interested in health issues including

enrolling to university courses to become nurses and doctors to save lives.

In Albania, alcohol and smoking, sexual health, obesity, mental health, substance misuse   are prevalent in Albanian youth. There is little discussion about mental health and sexual health due stigma associated to these issues.

According to  European Commission Albania  report( 2009), preventing Albanian youth from starting  smoking and refraining from alcohol abuse and unhealthy diets can contributing to  decreasing  poor health  among adults.

This project will be carried transnationally because health issues have no boundaries, and they are  affecting young people across Europe. The causes are the same, but the methodologies to address are not.

According to WHO Europe (2010), a common challenge identified by promoters of health services across Europe is how to engage young people in the activity or intervention on offer. This aims to address this gap  by creating a highly accessible  online  informal learning tool that will contribute to improving  the  health literacy  amount the youth.

Objectives

1. To promote good health among disadvantaged young people

2. To improve young people’s skills, experience, and knowledge

2. To increase youth workers and organisations’ capacity, competencies, and professionalism.

What results are expected during the project and on its completion?

•A multilingual 5-day one informal training module in form of syllabus with video presentation and infographics and text, pdf/PowerPoint version for download, for individual learning, and as a youth worker’s tool for training young people.

- About 500 young people, youth workers and youth organisations across Europe have been reached by the dissemination activities of the project.

- 40 young people  and peers have supported the research, design & testing of the training module  which will enable others to learn about how to prevent poor health.

- More than 200 people have attend multiplier events

- Over 150,000 people have been reached through online media, events, & dissemination of open-access resources

- A project report is produced containing the project activities, results, lessons learned and outcomes.

- A website containing the above project results.

In what way is the project innovative and/or complementary to other projects already carried out by the participating organisations?

The project is a new, young people-driven approach that moves from multiple project intervention about single health issue to an integrated approach based on a holistic view of young people.

The project is innovative because the results will be achieved through the participation of young people in community research activities resulting in  research findings that will contribute to

informing the development of the training module tailored to young people.

In addition to become more aware about their health needs, project participants working as researchers will increase their skills in research methodologies that will enhance critical thinking that could be useful in their education, entrepreneurship and employment prospects.

Particularly, this project is innovative because:

•It involves listening to the voice of young people ( through young people’s research activities), and how this will improve their health outcomes.

•The new online training module is co-designed with young people who contribute to its development.

Diversity Living Services ( UK):

This project will build on DLS ‘s current project ( Stand Up for Good Health and Wellbeing ) that is funded by the National Lottery Community Fund. The project activities include  raising awareness, providing training, coaching and information about health issues to disadvantaged adult BAMER (Black, Asian, Migrant, Minority Ethnic and refugee) communities in North London. A recent independent evaluation of the project has recommended DLS to promote good health among young people.

"Together for Life" (TFL)/ Albania  is a leader organization in health promotion and education in Albania. Since 2011, with support of the World Health Organization (WHO) TFL has founded the newspaper “Shëndet Plus” and the online platform www.shendeti.com.al, devoted entirely to issues related to health. This newspaper is providing continuous information to Albanian readers to have a direct contact with health care system and educate themselves about their health and their rights. TFL has implemented also several projects for promoting health education in schools, creating health promoting school models, supporting of the health care reform, informing and educating the teenagers about reproductive and sexual health etc.

Expert Pool/Bulgaria is actively involved in  the projects that aim at  engaging young people in physical activities for  better health. One of the current project is establishing sustainable mountaineering culture and promoting outdoor activity as a tool for overcoming various health and societal issues, including mental health.

PENHA /UK is implementing a four-year EU funded” Food We Want” development projects in UK in partnership with EU partners, International Institute for Environment and Development ( IIED), University College London (UCL), and Oxford Brookes University to increase youth awareness on sustainable agriculture and global food security issues. The project focuses on  promoting  young people’s healthy diet mong families with lower income.

How did you choose the project partners and what will they bring to the project? Does it involve organisations that have never previously been involved in a Strategic Partnerships

project?

The project brief was sent to all partners with a questionnaire based on the questions of the application form and other questions to identify the experience of each partner

organisations, the skills and experience of employees and the contribution the partners will bring to the project.

PENHA  ( UK)have never previously been involved in a Strategic Partnerships project. All partners were met with DLS staff at various Erasmus+ and ESC meetings to discuss the idea of this project.

How will the tasks and responsibilities be distributed among the partners?

•Diversity Living Services (DLS)  will be in charge of the preparation of  the Intellectual Output (the training module) and the overall project  coordination. They will prepare the overall project implementation plan.

•DLS will draft the training module based on the  contributions provided by each partner,  youth and health organisations, and young people research findings.

Each partner will research and draft a specific chapter as a contribution to the training module

•DLS will organise an end project conference ( multiplier event) to showcase the projects results including the IO.

Together for Life ( Albania) will be in charge of  the project publicity and dissemination of project results  using  the Erasmus+guide on dissemination and exploitation of results. They will also use  use  online and/or offline media connections and channels to support the project promotion at local, national and international level.  At the begining of the project, Together for Life l  will produce a Dissemination and Exploitation Plan of the project results.

PENHA ( UK)  will be in charge of monitoring and evaluation  of the project, planning and designing internal communication tools.  They will prepare a Monitoring and Evaluation Plan of the project.

Expert Pool (Bulgaria) will be in charge of young people’s involvement in the project activities ( research and volunteering) and will  work with young people to research the  baseline information required for monitoring . Expert Pool will design interview questionnaires that will be used by young people in research activities.

All partners:

•All partners will provide inputs to the preparation and design of the training module.

•Each partner will recruit and work with 10 young people as researchers and volunteers to identify young people’s training, information and advice needs that will inform the development of the online training module. Research activities will include interviews and surveys by and with young people, desk research and focus groups.

•Prior to research activities, the 10 young people will attend a one day in-house  organised by  each partner about community research methods.

•Each partner will analyse the research findings, with the aim of identifying important priorities and learning outcomes to be included in the draft of IO ( online training module).

•They will support young people in analysing and interpreting the research findings.

•Each partner will organise multiplier events that will take place in each country  to raise awareness about the project results.

If relevant, please identify and explain the involvement of associated partners, not formally participating in the project. Please explain how they will contribute to the implementation of

specific project tasks/activities or support the dissemination and sustainability of the project.

All partners are already working in collaboration with local youth, health, and training organisations which will comment on the draft of the training module, provide relevant information to its development and contribute  to the overall evaluation of the project activities and outcomes.

DLS is already working  UK  health voluntary organisations which regularly  deliver workshops to our service users. These organisations include Association for Nutrition, The British Obesity Society, Diabetes UK, Bowel

Cancer UK, HeartUK, Stoke UK, British Heart Foundation, Blood Pressure UK, British Dietetics Association, Post Box Nutrition, Obesity Health Alliance, Nutrition Society, Macmillan

Cancer, Dementia UK, University of Westminster. They have agreed to provide inputs on the draft of the IO ( online training module).

TFL has a long experience on working with the patient’s associations in Albania and provides assistance to them through the online platform https://propacientit.al/. TFL will partner with these patient’s associations, such as HOPE Albania, Patients with Hepatitis organization, Albanian Center for Population and Development (ACPD), Albanian Diabetes Association etc. during the implementation of the project.

Participants

Please briefly describe how you will select and involve participants in the different activities of your project.

The project will involve 10 young people,  health and youth organisations.

Each partner will involve  at least 2 health organisations and 2 youth organisations that usual work with each partner. They will form  the local  project steering group.

The recruitment of young people will be done through:

•Snowballing tactics and the use word of mouth referrals to target those who may not otherwise engage with existing support and services, This will involve encouraging  young people to recruit

other young people to join the project.

•Project summary presentations at schools, parent forums and youth centres.

•Off and Online application registration forms ( using Facebook and each partner’s website)

•The selection of eligible participants will be undertaken through telephone or face-to-face interviews to establish their interests, motivations and expectations in getting involved in the  project.

•The  project publicity fliers will be displayed in public places in most deprived areas where life expectancy is the lowest compare to the average national population’s life expectancy. These public places include youth and health organisations, hairdressing shops, community centres, youth centres, childcare centres, housing and social services waiting rooms, libraries, Doctors’ centres, churches and mosques and other places of worship, Internet café, supermarkets, cinemas, libraries, sport clubs, libraries and community organisations.

Young people  who will  take part in the research activities  will be invited by each partner to attend an in-house  training  workshop  about  community research methods, attend multiplier events,  manage social media and work as volunteers. They will also comment on draft online training module and take part in summarising the research findings.

How will you support these participants so that they will fully engage in the planned activities?

The project publicity material  and social media messages will include information about how young people  will benefit  from participating in the project such gaining transferable skills in research methods and administration tasks that will contribute to  improving their

CVs,  getting help with university applications,  and having access to information about job opportunities.

We will offer incentives to attend  multiplier events, and in-house workshop such as payment or refund for transport costs and lunch,  and refreshments.

We will work with parents and social services to find solutions to any problems participant young people are facing and that prevent them from attending. We will help them to access to specialist support when required

including housing, disability and mental health services, enrolling to further education, help them with CV writing, interview skills, providing information about internship, entrepreneurship and job opportunities and other opportunities offered by EU various  youth programmes.

Please describe briefly how and in which activities these persons will be involved.

•Each project partner will recruit 10 young people to take part directly in the project as volunteers and researchers.

•The young people will take part in-house training workshop organised by each partner about community research methods.

•After the training, these 10 young people researchers will take part in the project by researching, interviewing and recording experiences and aspirations of young people in relation to knowledge, awareness and access to health services.

•They will undertake outreach to publicise the project and  identify interviewees.

•They will carry out online and offline search about information background about health matters that are important to them.

•Each young person will carry out 3 open-ended interviews of 30-45 minutes each. The interviews will be audio taped and transcribed verbatim in  local language. They will analyse interview transcripts and summarised them in order to formulate the main messages and recommendations from the interview transcripts. The main messages will inform the development process of the online training module.

• Young people will also take part in volunteering activities such as managing social media by posting news and information about health issues and their research findings, organising local multiplier events, providing administration support,

desk research of information, participation in dissemination and marketing activities.

•2 Health organisations and 2 youth organisations  will participate in the local project steering group in each country to provide input to  the overall project implementation and  Intellectual Output.

Preparation

Preparation:

Please describe what will be done in preparation by your organisation/group and by your partners/group before the actual project activities take place, e.g. administrative

arrangements, communication about the activities, selection of the persons, coaches, involvement of stakeholders, etc.

Administration and Coordination:

•The project Coordinator will send the grant agreement to all partners.

•All partners will sign a partner agreement setting out their roles, summary of project activities, project outputs and outcomes and monitoring and evaluation arrangements.

• Each  project partner will appoint the local coordinator of the project who will be the main contact of the project at the national level.

•A  quarterly review of the budget required will be undertaken in collaboration with each partner and any changes in budget allocation will have to be first authorised by the UK NA.

•Each partner will communicate to the coordinator the details of the people who will be directly involved in the implementation of the project.

•Each partner will submit quarterly reports to the Project coordinator. Project partners can ask any time questions about how to resolve problems and about project implementation.

•A dissemination plan and multiplier event agenda will be agreed by all partners.

Communication arrangements:

Communication channels between partners will be agreed.

Transnational meetings will take place every 6 months ( if covid-19 is no longer a barrier to do  meet face-to-face). ZOOM meetings and online email communications will  regularly take place ( each time this is required) between partners to discuss obligations,  project implementation strategies and practices, monitoring and evaluation, reporting, financial management and accountability and the preparation of the Intellectual Output.

Communication beyond the project

partner team will be undertaken through social media ( Facebook and Twitter). Young people, youth workers, health organisatons, and youth organisations  and anyone interested in the project will be invited to subscribe to an e-newsletter to receive project  updates and the project website. The project updates will be featured in the blog of the project website.

Google drive will be used for communication and collaboration, including sharing documents, work, requesting contributions and storing partner contributions and updates.

Project Management:

Each partner organisation will create a Project Steering Group comprising of 5 people representing  young people, youth workers, health professionals, and training organisations. These groups will regularly discuss and evaluate the project implementation and outcomes and provide support the national project coordinator in project planning, the development of clear and realistic internal objectives, targets, achievable indicators and work plans.

Project folders will are prepared by each project partner to contain the project agreement, the Project Logical Framework, schedule and nature of interim and final reports; project

management plan (including Quality Plan, Risk management plan); dissemination plan, work plans and evaluation forms; financial expenditure plans and records including receipts and invoices, minutes of transnational and online meetings; press releases, photographs, brochures, leaflets, e-newsletters and videos of events.

Human resources and Participants:

Each Project Partner will identify and recruit and/or nominate project team members for  the implementation of the project activities. Each  employee involved in the project will  have a job description that will be  communicated to all partners. Weekly meetings of project employees involved in the project will take place to review and plan the project activities.

https://www.cio.com/article/3091119/6-proven-project-team-communication-strategies.html

https://www.workfront.com/blog/10-ways-project-management-can-improve-with-communication

Management

Funds for Project Management and Implementation

Funds for 'Project Management and Implementation' are provided to all Strategic Partnerships based on the number of participating organisations and duration of the

project. The purpose of these funds is to cover diverse expenses that any project may incur, such as planning, communication between partners, small scale project

materials, virtual cooperation, local project activities, promotion, dissemination and other similar activities not covered by other types of funding. A partnership may receive a

maximum of 2750 EUR of 'Project Management and Implementation cost' per month

Funds for Project Management and Implementation

Please provide detailed information about the project activities that you will carry out with the support of the grant requested under the item 'Project Management and Implementation

The  project management funds will be used for the following activities:

- To cover partners’ time for project coordination and activity planning/implementation at local and transnational level.

- This may include organising  face-to-face virtual meetings including transnational meetings.

- Publicity, stationary and printing, communication expenses.

- Convening stakeholders’ meetings and local multipliers events.

- Supporting and supervising young people’s research and volunteering activities.

- Planning and scheduling project activities including events.

- Monitoring project activities, outputs and outcomes.

- Implement  the dissemination plan.

- Communicate with funders, responding to queries from the public, and stakeholders

- Reviewing documents and establishing and maintaining the project documentation and records.

- Meetings – preparing the agenda, taking minutes, and sharing, follow-up notes.

- Researching information required to achieve the project objectives.

- Recruiting volunteers and project workers

Transnational Meetings

Transnational project meetings: how often do you plan to meet, who will participate in those meetings, where will they take place and what will be the goal?

We plan 4 Transnational Meetings, in Months 2 (kick-off meeting), 8 ( 2nd meeting), 14 (3rd meeting) and 22(4th meeting) attended by the project partners.

The 1st will be the Kick-off meeting in London UK that will review the UK NA grant agreement, monitoring and evaluation requirements, project implementation plan, publicity and dissemination, financial management, partners’ roles and

responsibilities, planning of transnational meetings, young people’s participation,  and contribution to intellectual outputs.

The 2nd will be in (Bulgaria) to review the research findings and how they inform the development of the training module.

The  meeting will  review the draft of the training module and the project agreed implementation strategies.

The 3rd will be organised in Albania to review the progress made in achieving the overall project results, and finalising  the training module.

The 4th meeting will take place  in London to showcase the project results in end project conference.

Project Management:

How will you ensure proper budget control and time management in your project?

Overall, our financial policy and monitoring system includes regular checks against budget heads; quarterly financial reports to reconcile project progress against plan, outputs and

budget; financial transaction evidence recorded and identifiable to ensure easy bank reconciliation; rigorous application of Charity Commission and Companies House requirements.

We will apply our financial policy and monitoring system includes the following main procedures:

•Checking regularly that we do not exceed the amount allowed for each budget line before committing any expense.

•Producing quarterly financial reports which enable us reconcile project progress against plan, outputs and budget.

•All financial transaction evidence are kept, recorded and are identifiable to ensure easy reconciliation with the bank statement.

•A written invoice will be required for all purchases

•At least two competitive quotations must be obtained prior to the purchase of any equipment or other items costing more than £500.

•All payments made will be evidenced by invoices, receipts, bank statements and copies of cheques issued.

•Two signatories must sign all cheques and cash withdrawals.

•The project audit will be shown separately in the organisation audited annual accounts which are produced on the basis of Charity Commission and Companies House rules.

•A certified accountant is approved by the AGM every year to produce annual accounts.

All partners will follow the above financial procedures. All partners will produce and share financial quarterly report. Virtual meeting between partners will take place to review these reports.

Project staff and volunteers will meet on weekly basis to review the project work of the previous week and to plan for the next week. Diaries of  the following project activities and dates of

completion of the project deliverables will be agreed at project team weekly meetings. All project partners will set up the calendar of the completion of the project deliverables. Partners will complete the timesheets about the  completed activities.

How will the progress, quality and achievement of project activities be monitored? Please describe the qualitative and quantitative indicators you will use. Please give information about

the involved staff, as well as the timing and frequency of the monitoring activities.

- At the start of the project, we will design the project logical framework to set SMART  objectives, targets, outcomes, outputs and have milestones, against which achievements of project activities will be reported to every 6 months.

- Qualitative indicators will show participants’s opinions, views and experiences about the quality  of the  expected project results.

- Quantitative indicators will show the numbers of people involved or benefiting from the project,  the number of people who have been reached by the dissemination activities, the changes that have resulted from the intervention of this project and the main tangible project  results.

- Each partner will produce a 6-month report about the progress that include  the indicators that have been achieved for each project activity. This report will be shared with all partners.

- Each partner will ensure that all  new project paid staff and volunteers are recruited and selected on open and competitive basis through adverts in relevant job portals and newspapers.

- Each partner will make sure that existing employees have  the skills and competencies to undertake additional responsibilities in relation to this project and  their job descriptions clearly outline their roles.

- Every three months, project staff and regular partner’s virtual meetings will take place to review the implementation of the project plan outlined in the project logical framework.

- As we have been involved in training delivered by Salto-Youth trainers, we will  request them to comment on the draft of the training module. Health,  and youth organisations and teachers will also be contacted for providing inputs to the training module.

- The training content will be developed using authoritative resources and each lesson will include references.

How will you evaluate to which extent the project reached its results and objectives? What indicators will you use to measure the quality of the project's results?

Baseline information in relation to  young people’s health needs and socio-economic barriers will be established using focus groups, interviews, feedback forms, desk research undertaken by the project partners with the participation of young people carrying out  research activities to compare with  the project expected outcomes.

The project evaluation will used internal monitoring records, project reports and interviews with project participants.

Interviews with  young people, youth and health organisations will be carried to collect their views about the quality of the training module and how the implementation of the project was progressing.

The following indicators will be used in  the project evaluation:

• At least 80% of participants report that they have increased their  skills and knowledge  in relation managing poor health (demonstrated by  feedback forms completed by young people).

•80% of participants report that their  confidence and self-development in relation to moving toward employment, entrepreneurship and further education or training have increased (demonstrated by  feedback forms completed by young people).

•At least 80 % of targeted groups  report  that the dissemination information has reached them(demonstrated by  feedback forms completed by young people)..

•At least 80 % of targeted groups  report that the quality of information produced and disseminated is good( demonstrated by the online reviews)

•At least 80 % of  website users   report that the quality of training module is good ( demonstrated by the records of the reviews/ratings of the IO  by users).

•At least 80 % of  participants report that the multiplier vents were useful, informative and well organised (demonstrated by feedback forms completed by  participants).

•The number of downloads of the training module,  the numbers of enrolment to the online training module, the number of views of the video ( demonstrated by Google analytics and  website tracking  records).

•The number of youth workers and youth organisations who have express their interest in using the online training module (  demonstrated online feedback forms).

What are your plans for handling risks which could happen during the project (e.g. delays, budget, conflicts, etc.)?

The project coordinator (UK) prepares the  a draft Project Logical Framework  as a project planning tool that show the activities, outcomes, monitoring and evaluation, and milestones of the project clearly to be used and revised at the kick-off meeting.

Each partner will manage the risks using the project Logical Framework and by weekly project meetings to predict, document, analyse, prioritise , remove or mitigate any risk that would impede the implementation of the project.

We will plan a response by developing a contingency plan or preventative measures for each risk.

The response may include review staff roles, proper allocation of resources, working more as a team to respond to specific risks, more marketing, changing timing and location of

events, and seeking appropriate advice and authorisation from the UK NA.

If there is low attendance of the participants to events and workshops, we will examine our publicity strategy and make the required adjustments.

If there is a partner who decide to withdraw from the project, we will inform the UK NA about the situation and the option available to continue the project by passing on the activities to

the project coordinator, another partner or a new partner. If a partner is not meeting the expectations, we will try to resolve the problem with them, support them or/and propose the UK NA to withdraw them from the project.

Implementation

Please explain how will the project activities lead to the achievement of the project objectives and delivery of the planned results

Objective 1: To promote good health among disadvantaged young people.

Objective 2: To increase youth workers and organisations capacity, competencies and professionalism.

The above two objectives will be achieved by the use of the  online training module as the main IO to be created by this project ( described in in IO section below-Output Title 01).

The training module will be uploaded online using LearnPress, a Learning Management Software which is a comprehensive  LMS Plugin for WordPress, just like WordPress Moodle.

This plugin can be used to easily create & sell courses online. Each course curriculum can be made with lessons & quizzes which can be managed with easy-to-use user interface.

With this WordPress LMS plugin, you can quickly and easily create education, online school, online-course websites with no coding-knowledge required.

The course video will be created using  Doodly video creator  software.

The training module will cover the following topics:

- Understanding health inequalities

- Understanding healthy lifestyles

- Understanding and preventing Alcohol Misuse

- Enjoying physical activity and understanding how it is good for your health

- Understanding Healthy Weight and Healthy Eating and how to achieve them

- Understanding Sexual Health

- Understanding the health consequences of smoking and the steps to quit

- Understanding the health, economic and social consequences of Substances Misuse

- Understanding Mental Health

- Understanding covid-19 and how to prevent it.

Objective 3: To improve young people’s skills, experience, and knowledge

•Each partner will involve  10 young people as volunteers who will undertake research ( desk research and surveys among peers) into the content of the training module by consulting other young people to identify the priority issues to be addressed by online training module. Prior to undertaking research activities, young people will attend a one-day training workshops about community research methods. This training will contribute to improve young people’s skills, knowledge, confidence resulting in better educational and  employability prospects.

The training module will be co-designed with young people as researchers and informants. This new method of reaching disadvantaged young people is involving young people as

the researchers to identify the priorities and the needs of their own training in addition to their contributions to the design and testing of the training module.

Please describe the division of work, the tasks leading to the production of the intellectual output and the applied methodology

•Diversity Living Services (DLS)  will be in charge of the  preparation of the training module. The preparation will involve a steering group  of health organisations  to provide inputs in the draft of the training module.

•These organisations are already working with DLS in implementing a health project funded by  the National Lottery Community Fund.

•The team will listen and consider the inputs from the  young people’s research findings and from the project partners.

• DLS will be in charge of the technical aspects in relation to designing the website, the LMS and the course video.

All partners:

- Each partner will work with recruit and work with 10 young people as researchers to identify the training and advice needs that will be the basis to develop the training module.

- Prior to research activities, the 10 young people will attend a one-day training in community research methods.

- Partners will analyse the research findings, with the aim of identifying important priorities and learning outcomes to be included in the draft of the training programme.

- They will support young people in analysing and interpreting the research findings.

- Each partner will select one or more topics from the list outlined in the precedent question.

The training module will be developed using the  SALTO-YOUTH’s guide ( “Curriculum Development Canvas)” about how to prepare informal curriculum for youth education.

- Identify the scope of the content of the curriculum material

- •Involve young people through volunteering, research and providing feedback to the draft training module

- Define SMART Objectives - Which goal? - Where do we want to get? - What would be possible outcomes of the module? - Are our objectives SMART?

- Outline your overarching topics and timeline. Each partner will choose the topic to develop in lessons.

- Plan the sequence in which the content will be presented and what delivery method to use. Research, search for appropriate materials, and decide what graphics to use.

- Outline the content, including knowledge, attitude, and skills learners will be able to acquire through participating in the planned curriculum activities. What should people learn during the module?

- Write the lessons to provide a comprehensive youth learning experience.

- Create or attach a variety of assessments to the lessons.

- Determine what materials and resources you’ll need, e.g. resources or student guides you want to include for each lesson

- What are the learning Outcomes - What methods are we going to use to record and validate learning outcomes?

- The partner in charge of the coordination of the IO tracks all team members’ changes and ensures that they incorporate all necessary edits and revisions

- The partner in charge of the coordination of the IO  pulls  everything together into an participatory and professional training module ( text and pdf)

- Evaluation - What works? - Which are the expected outcomes? - How do we know we have accomplished them? - How do we measure the outcomes?

- The essential messages of each topic  of  training module are presented in video and power point.

How will you communicate and cooperate with your partners?

Our transnational communication will be face-to-face at transnational meetings and multiplier events and otherwise via email, phone, quarterly project updates posted on social media, Google Drive and Skype or zoom.

Virtual meetings will take place at any time at the request of any partner.

Each  partner will share their activities, documents and reports on Google  drive.

Each partner will have a lead person able to communicate in English and to maintain communication with the project coordinator and other partners to respond to the requests from

partners for information and/or action and to provide updates about the project implementation.

Communications between partners and

participants and stakeholders not directly involved in the implementation of the project will be done by email, the website and the project social media pages (Facebook and Twitter). The website will have a feature enabling anyone interested in the project to subscribe to the project newsletter that will provide updates about the progress of the implementation of the project.

Output  Title 01

Output Description (including: needs analysis, target groups, elements of innovation, expected impact and transferability potential)

This proposal contribute to the implementation of the EU Youth Strategy that aims to support the health and well-being of young people.

The  project needs analysis  shows that  alcohol and smoking, sexual health, obesity, mental health, substance misuse   are prevalent in  European youth.

A common challenge identified by promoters of health services across Europe is how to engage young people in the activity or intervention on offer and how  young people can have the

opportunities to have  a say on and access to the information and the services  they need  to prevent poor health.

This project is innovative because it involves listening to the voice of young people in order to design the training methods that will contribute to improve their health outcomes.

The tangible Intellectual Output is an interactive and participatory multilingual 5-day online training module.

The full training module  ( text/power point and video) will be available  on the project dedicated website to download online and to use in face-to-face training by youth and health organisations from any country. Young people will use it for self-learning about  how to prevent unhealthy behaviours and lifestyles.

Multiplier Events

Event Description (Including : Targets groups and objectives)

Each partner will organise face-to-face multiplier meetings that  in the middle of year two of the project. Each meeting will be attended by 100 people.

An end project conference will be organised in London. The conference  will be a high profile event that will be attended by youth organisations, youth workers, health and youth organisations, and training organisations. The meeting will aim  to showcase the training  module. The event will be publicised at Eventbrite website.

Follow Up

Impact

What is the expected impact on the participants, participating organisations, target groups and other relevant stakeholders?

The monitoring and evaluation records will show that:

Participants and target groups:

a)To promote good health among disadvantaged young people (Objective 1)

•By the end of the project, at least 75 % of young people participants report that they have increased their skills and knowledge of health issues and self-management of care, resulting

in improved health.

•At least 75% of young people of  who have had enrolled to the online training module for self-learning  will have adopted healthy lifestyles and behaviours, resulting in being more physically healthy and active.

•After three years from the end of the project, at least 75% of young people who have enrolled to the online training module leading to  increased health literacy, understanding of  the benefits of a healthy lifestyles, abilities to  make healthier choices, and knowledge of risks of unhealthy behaviours.

b) To increase youth workers and organisations’ capacity, cooperation, partnership working, competencies and professionalism (objective 2)

The training module will have impact beyond  partner organisation because youth, training, schools and health organisations elsewhere will use it for training young people.

•At the end of the project all the health professionals, youth workers and youth organisations report that the training module will contribute to their professionalism in delivering training, support and advice to young people about health issues.

•After three years from the end of the project 80% of the above stakeholders report that the online training module is an effective tool to deliver informal training for  young people with few opportunities.

c)To improve young people’s skills, experience and knowledge (Objective 3)

•By the end of the project at least 75% of young people ( 10 participants per each partner) will have improved employment or self-employment prospects, enhancing their CVs to apply for

jobs in health and care services, customer service, etc; progressing to further education and training in health and social care; or otherwise entering the labour market and/or getting professional help in taking their next step.

What is the desired impact of the project at the local, regional, national, European and/or international levels?

At local level:

•Young people will have increased the skills and knowledge about health issues to help their families, friends and relatives. These skills will motivate them to undertake voluntary

activities in NGOs, health organisations and public sector.

•Young people become are committed to participate in active citizenship and notably volunteering and solidarity activities

•Young people will have increased confidence to prevent poor health. They will be able to influence the attitudes and behaviours of their peers, family members and local residents with

regard to these issues, so they in turn are more aware and better informed.

•Young people will have acquired skills and knowledge to influence the policies and practices of local community groups, health and youth organisations and local authorities (through participation in youth assemblies and forums) to ensure these institutions adjust their services and practices to meet young people health needs.

At regional/national level:

Heath and youth organisations will have learned the barriers young people are facing in accessing to healthcare and will ensure that lessons learned from this project inform the

development of health services and policies that meet young people needs, including the passing of new legislation and making available new investment to work to reduce health

inequalities that affect disadvantaged young people.

At the European and international levels, the project lessons learned ( project report), young people’s research findings,  and  the training module will be a successful case study that will be used by NGOs, international organisations including WHO to affectively plan and deliver health projects for young people.

Through young people’s research findings

We expect the project to be an exemplar as to what can be achieved through active citizenship in Europe, supporting young people to express themselves and spread their message

along Europe, so raising visibility about their ideas, concepts and views.

The project results will contribute to influencing policy and programmes development in relation with better inclusion of young people in health services provision at national and European institutions.

The project will bring about an increased quality of training, cooperation networking and sharing of solutions in Europe for NGOs in providing youth training and self-development.

How will you measure the previously mentioned impacts?

Both qualitative and quantitative data will be collected because a combination of the two may result in the most convincing evidence of impact. We will produce the project logical framework that will help us to decide what we want to measure and how we will collect the information and data we need. It will include

activities, measuring methods, indicators, milestones and outcomes.

It will enable us to ensure that the project is proceeding as planned; collect accurate, timely and well-evidenced information that will alert us if we need to take action to ensure that the

project stays on track and to enable us to complete claims; demonstrate to funders that outputs and outcomes have been met in accordance with the contract; and inform stakeholders of progress. The evaluation will start from the beginning of the project so that we can track progress over time.

Two months before the end of the project and 3 years after, a survey will be carried to identify the impact of the project on the participants,  target groups and other relevant stakeholders.

The training module will include the  feedback questions to be completed by young people who enrolled to  the course for self-learning and for organisations for providing their feedback on the quality and relevance of the training module.

We will undertake customer satisfaction surveys to get feedback of the project beneficiaries through telephone interviews of a sample of project participants, partners, health and youth

organisations and other stakeholders.

Further evaluation will be carried through online questionnaires and focus groups.

We will develop evaluation questions based on the project objectives and expected outcomes described in the above sections.

Which activities will you and your partner carry out in order to share the results of your project beyond your partnership?

In order to ensure proper project results dissemination, a dissemination plan will be created and will be followed before, during and after the project implementation.

The project partners will publish information in their national languages about the project activities and results on regular basis in their organisation’s web pages, both before, during

and after the implementation of the activities.

As part of the dissemination activities each partner will promote project activities and results to youth workers, youth organisations and health organisations through the website and social media ( Facebook and Twitter).

The publicity  of the project of the project activities and results will be provided at different levels:

•Each partner will publish a booklet of the project results that will be displayed in schools, colleges and universities, health organisations and practitioners’ offices, public spaces such

as libraries, local authority meetings rooms and halls.

•Each partner organisation will promote the project through its already existing communication tools such as: website  and social media platforms.

The overall methodology for dissemination includes:

BEFORE the project starts:

•We will produce the dissemination and exploitation plan with agreed expected impact and deliverables.

DURING the project:

•We will use multiplier events, contact the media, make presentations in third party meetings, workshops, seminars and conferences, use of social media, website and email bulletin

AT FINAL REPORTING STAGE:

•We will upload the final project results on the project website and  on the Erasmus+ Project Results Platform and other websites of organisations working with young people.

•We will present the project results at the end project conference

AFTER the project:

•The website  that will feature the project  results will be maintained.

• SEO ( Search engine optimisation) will be carried out on the website to ensure better ranking on the first page in Search engines.

Who will be responsible for the dissemination activities within your partnership and which specific expertise do they have in this area? What resources will you make available to allow

for the proper implementation of your dissemination plans?

Together for Life has been chosen because of their expertise in managing and disseminating results of many EU funded youth projects. With a long experience in implementing Erasmus|+project, Together for Life has developed personal contacts and a vast network of private, not-for-profit organisations as target groups for dissemination.

The project technician funds will be used for   covering the IT aspects of dissemination activities. At EU and international level, Together for Life will use different dissemination tools including the project  website,  social media and contacts with the media ( Facebook and Twitter) in addition to multiplier events. The funds for  technical support to design the project and carry out  SEO( Search Engine Optimisation) have been included in the budget.

Together for Life (Albania) will be responsible for the project dissemination. Together for Life has a strong media and communication component within the organisation. It owns a print format newspaper dedicated to health (https://shendeti.com.al/) that is distributed all over Albania and Kosovo, and has more than 100,000 followers online https://www.facebook.com/shendetionline/?ref=bookmarks and 4 online platforms.

All the materials that will be produced in the framework of the project will be published on TFL’s website https://togetherforlife.org.al/ and disseminate through social media https://www.facebook.com/TogetherforlifeAL/, print format newspaper (Shëndet +), TFL’s newsletter (has more than 2500 subscribers) in “Youth Voices” Network of Organizations online platform www.jotabu.al (a portal that is followed by teenagers all over Albania and is offers safe and accurate sexual and reproductive health for young people).

Erasmus+ has an open access requirement for all materials developed through its projects. If your project is producing intellectual outputs/tangible deliverables, please describe how

you intend to ensure free access for the public to a digital form of this material. If you intend to put any limitation on the use of the open licence, please specify the reasons, extent and

nature of this limitation.

In order to achieve a wider access to the project materials, the partnership will publish the project results on the project website and partners' websites.

The printed version of the online training module ( text, pdf and Power Point) will be available online for free downloading. The online  video version of the training module, which is part of the training module be available on the website as well.

How will you ensure that the project's results will remain available and will be used by others?

A dedicated website for the project will host the project results  for at least for 10 years or indefinitely. The project results will also be available at Erasmus+ Project Results Platform. The online training module will be

available across all mobile devices and apps. The website  will be registered to different  directories in relation to health and youth including advice and training directories.

If relevant, please provide any other information you consider appropriate to give a full understanding of your dissemination plan and its expected impact (e.g. how you have identified which results are most relevant to disseminate; how you will ensure the involvement of all partners; how you see synergies with other stakeholders, etc.)

The main output for this project is the training programme as a tool for youth organisations to deliver training for young people. The 2nd output is a report about young people's research

findings that will contribute to raising awareness about the problems they face at local national and Europe Level. These findings will  be publish for a wider access by the public

and all stakeholders working with young people. Project partners will disseminate these

outputs during and after the project via their websites, their local and national networks. This is part of the project agreements the project coordinator will sign with them. We will share

the project results with diverse stakeholders including youth organisations, health organisations and professionals across Europe using online tools and through multiplier events. The synergies with other stakeholders will be achieved by implementing cooperation activities for training young people using this training module and by referring other stakeholders to the results of this project.

Sustainability:

What are the activities and results that will be maintained after the end of the EU funding, and how will you ensure the resources needed to sustain them?

•As a co-funding project, the partners will continue to use their own resources to ensure the projects results are continuously accessible online.

•This proposal will be used to seek further funding to transfer its methodologies to  improve informal learning in other areas such as technology, employment, entrepreneurship, marketing, democracy and politics, climate change, sustainable development.

•The training module will be used by interested parties to fundraise for delivering training to young people.

•The training module and supporting video are available online and is accessible by the public and organisations.

•The lessons learned and methodologies will be used to design similar projects.

•The skills acquired by participants and the professionalism acquired by partners and youth organisations constitute a long term investment in participants and organisations.

•The online training module will be accessible 24/7 for at least 10 years after the duration of the project.

•The online training module will be an ongoing tool for use by the youth organisations, schools, colleges, youth trainers and others working in the field of youth.

•The lessons learned will be used to foster the learning in training young people to improve their awareness and understanding of health

Improvement among young people.

Summary:

The Youth Health Boost Project is a two-year innovative initiative implemented by four partners from UK, Bulgaria and Albania.

This project targets disadvantaged young people as those aged between 13 and 25 years old, including young people migrants, refugees and minority ethnic communities.

The project objectives are to improve   young people’s skills, experience and knowledge, to promote good health among disadvantaged young people and to increase youth workers and organisations’ capacity and competencies in delivering informal training to young people.

This project has been developed with the premises that all children and young people deserve a healthy start in life. This will help them to reach their full potential throughout their young lives and as they grow into adults. Giving every young person a healthy start is fundamental to creating a more equal inclusive  society.

The project uses new methods of reaching out hard-to-reach disadvantaged young people by listening to their voice to improve their health outcomes by involving young people as the main researchers  to identify their needs, concerns, and aspirations in accessing health care services.

The 1st main project result (intellectual output) is a 5-day online training module comprising of a syllabus ( text and PowerPoint) and video.

Findings from community research activities planned and carried out by young people and the inputs from health and youth organisations will inform the development of the online training module.

The project will contribute to promoting quality youth work by resourcing youth workers to improve their competencies, knowledge and skills to deliver relevant and appropriate training to disadvantaged young people. It will also contribute to changing young people’s behaviours that  may contribute to potential pour health.

Through community research activities, young people will acquire increase transferable skills and knowledge that enable them to enter in labour market, entrepreneurship or enrol into further education to become health professionals or embrace other allied professions.